## INFRASTRUCTURE & PLANNING
KEY PERFORMANCE AREA 1: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
DEPARTMENT | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY MEASURABLE PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGETS |  |  |  |  | QUARTERLY TARGETS |  |  |  |  | CORRECTIVE MEASURES TO BE TAKEN
[6 empty] | QUARTER 1 |  |  |  |  | QUARTER 2
[6 empty] | Target | Actual Achievement | Budget | Means of verification | Reason of Variance | Target | Actual Achievement | Budget | Means of verification | Reasons of Variance
Objective:
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 39 households through rural electrification projects for year ended June 2023: Emalangeni Phase 2Ward 5 | Phase 1 | 1.1.1.1.(a) Number of households connected through rural electrification at Emadlangeni Phase 2 , ward 5 | 39 connections at Emadlangeni Phase 2, ward 5 | Site establishment | NOT ACHIEVED | 450000 | Quarterly Progress Report | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. | Construction | NOT ACHIEVED | 450000 | Quarterly Progress Report | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. | DESIGNS WERE RECOMMENDED FOR REVISION. ONCE APPROVED THE TARGET WILL BE MET
Infrastructure and Planning Development | Basic service delivery and infrastructure development | To ensure that procurement of services is concluded within 90 Days (Bids) | New Indicator | 1.1.1.2 Percentage of Bid awarded within 90 Days (per 80/20 procurement process) | 100% | 100% Bid Awarded | ACHIEVED |  | Tender Register/Listing & Appointment Letters |  | 100% Bid Awarded | NOT ACHIEVED |  | Tender Register/Listing & Appointment Letters | DELAYS IN CONVENING BID COMMITTES | PROCESS WILL RESUME AFTER THE BID COMMITTEE CONVENES
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 61 households through rural electrification projects for year ended June 2023: Chanceni Phase 2 Ward 5 | Phase 1 | 1.1.1.1.(b) Number of households connected through rural electrification at Chanceni Phase 2, ward 5 | 61 connections at Chanceni Phase 2 | Site establishment | NOT ACHIEVED | 800000 | Quarterly Progress Report | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. | Construction | NOT ACHIEVED | 800000 | Quarterly Progress Report | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. | DESIGNS WERE RECOMMENDED FOR REVISION. ONCE APPROVED THE TARGET WILL BE MET
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 12 households through rural electrification projects for year ended June 2023: KwaNtaba Phase 3Ward 4 | Phase 2 | 1.1.1.1.(c) Number of households connected through rural electrification at KwaNtaba Phase 3, ward 4 | 12 connections at KwaNtaba Phase 3 | Site establishment | ACHIEVED | 551000 | Quarterly Progress Report |  | Construction | ACHIEVED | 551000 | Quarterly Progress Report
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 17 households through rural electrification projects for year ended June 2023: | Phase 2 | 1.1.1.1.(d) Number of households connected through rural electrification at Kaarpoort Phase 3, ward 4 | 17 connections at Kaarpoort Phase 3 | Site establishment | ACHIEVED | 591250 | Quarterly Progress Report |  | Construction | ACHIEVED | 591250 | Quarterly Progress Report
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 74 households through rural electrification projects for year ended June 2023: Blue Mountain Ward 4 | 0 | 1.1.1.1.(e) Number of households connected through rural electrification at Blue Mountain, ward 4 | 74 connections at Blue Mountain | Site establishment | NOT ACHIEVED | 1 172 250 | Quarterly Progress Report | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. |  | NOT ACHIEVED |  |  | TARGET WAS NOT MET BECAUSE THE DESIGNS WERE NOT APPROVED BY THE ESKOM STAKEHOLDERS. | DESIGNS WERE RECOMMENDED FOR REVISION. ONCE APPROVED THE TARGET WILL BE MET
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Connection of 180 households through rural electrification projects for year ended June 2023: Wit Umfolozi Phase 2 Ward 6 | Phase 1 | 1.1.1.1.(f) Number of households connected through rural electrification at Wit Umfolozi, phase 2 ward 6 | 180 connections at Wit Umfolozi, phase2 | Site establishment | ACHIEVED | 608750 | Quarterly Progress Report |  | Construction | ACHIEVED | 1 172 250
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Rehabilitation of Kerk street 0.7 km phase 3 for year end 30 June 2023 | Kerk Phase 2 | 1.1.3.2 Percentage rehabilitation of 0.7 km kerk street phase 3, ward 2 | 100% Rehabilitation of 0.7 km, Kerk street phase 3, ward 2 | SCM Processes (Specification, Evaluation and Adjudication) | NOT ACHIEVED | - | Advert and minutes & attendance register for all Bid Committees | DELAYS IN CONVENING OF SCM COMMITTEE |  | NOT ACHIEVED |  |  | AWAITING APPOINTMENT OF SERVICE PROVIDER | THE PROCESS WILL CONTINUE AS SOON AS THE SCM COMMITTEE CONVENES.
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Length of roads levelled through road maintenance program in the 2022/23 Financial Year | 60KM | 1.1.3.3 100% maintenance of 60 km of roads in all 6 Wards | Maintenance of 60 KM on municipal roads | Ward 1 (5 KM) Ward 2 (5 KM) Ward 3 (5 KM) | ACHIEVED | 100000 | Quarterly Report and Ward councilor’s letter |  | (5 KM) Ward 5 (5 KM) ward 6 (5 KM) ADD WARS | ACHIEVED | 608750 | Quarterly Report and Ward councilor’s letter
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 Reviewed and Adopted 2022/23 Housing Sector Plan | 1 | 1.1.4.1 Number of adopted Housing Sector Plan | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 Reviewed and adopted 2022/23 Spatial Development Framework | 1 | 1.1.4.2 Number of adopted Spatial Development Framework | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 Conduct 2022/23 ERF 750 Cemetery Hydrological study | 0 | 1.1.4.3 Number of ERF 750 Cemetery Hydrological study conducted | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Review and adopt LED strategy | 0 | 1.2.2.1 Number of reviewed and adopted LED strategy | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Review and adopt tourism strategy | 0 | 1.2.2.2 Number of reviewed and adopt tourism strategy |  |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | Provide 4 capacity building interventions for entrepreneurs and SMME’s | 0 | 1.2.3.1 Number of capacity building interventions for local entrepreneurs and SMME’s provided | x4 | x1 | ACHIEVED |  | Invite/ training manual & attendance register |  |  | ACHIEVED
Infrastructure and Planning Development | Basic service delivery and infrastructure development |  |  | 1.2.3.2 Refurbishment of Balele Game Park | X4 | X1 | ACHIEVED |  | Progress Report |  |  | ACHIEVED
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 4 Disaster Management Advisory Forum Meetings to be conducted in the 2022/23 Financial Year | 4 | 1.2.4.1 Number of Disaster Management Advisory Forum Meetings conducted | x4 | x1 | ACHIEVED | - | Notice, Agenda, Minutes & attendance register |  |  | ACHIEVED |  | Invite/ training manual & attendance register
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 20 lightning conductors to be installed in the year ending June 2023 | 0 | 1.2.4.2 Number of lightning conductors purchased | x20 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER |  | Progress Report
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 2 Reviewed and updated contingency plan for 2022/23 financial year | 2 | 1.2.4.3 Number of Reviewed and updated contingency plan for 2022/23 year | x2 | x1 Summer season | ACHIEVED |  | Plan and Council resolution |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 8 Disaster Management trainings & awareness campaigns conducted in 2022/23 | 0 | 1.2.4.4 Number of Disaster Management trainings & awareness campaigns conducted | x8 | x2 | ACHIEVED |  | Report & Attendance register |  | x2 | ACHIEVED | - | Notice, Agenda, Minutes & attendance register
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 review & adopt Disaster Management Plan in the year ending in June 2023 | 1 | 1.2.4.5 Review & adopt Disaster Management Plan | x1 |  | NOT DUE THIS QUARTER | - |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 Review & Update Disaster Management Sector Plan in the year ending in June 2023 | 1 | 1.2.5.1 Review & Update Disaster Management Sector Plan | x1 |  | NOT DUE THIS QUARTER | - |  |  |  | NOT DUE THIS QUARTER
Infrastructure and Planning Development | Basic service delivery and infrastructure development | 1 Monitoring of construction of Disaster Management Centre | 0 | 1.2.5.2 Monitor construction of Disaster Management Centre | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER |  | Report & Attendance register

## CORPORATE SERVICES
KEY PERFORMANCE AREA 2: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION
DEPARTMENT | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY MEASURABLE PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGETS |  |  |  |  | QUARTERLY TARGETS |  |  |  |  | CORRECTIVE MEAUSRES TO BE TAKEN
[6 empty] | QUARTER 1 |  |  |  |  | QUARTER 2
[6 empty] | Target | Actual Achievement | Budget | Means of verification | Reasona of Variance | Target | Actual Achievement | Budget | Means of verification | Reasona of Variance
Objective:
Corporate & Community Services | Basic service delivery and infrastructure development | To ensure that procurement of services is concluded within 90 Days (Bids) | New Indicator | 2.1.1.1 Percentage of Bid awarded within 90 Days (per 80/20 procurement process) | 100% | 100% Bid Awarded | ACHIEVED |  | Tender Register/Listing & Appointment Letters |  | 100% Bid Awarded | NOT ACHIEVED |  | Tender Register/Listing & Appointment Letters | DELAYS IN CONVENING BID COMMITTES | PROCESS WILL RESUME AFTER THE BID COMMITTEE CONVENES
Corporate services | Municipal institutional development and transformation | Review and adoption of 5 polices | 5 | 2.1.2.1 Number of adopted reviewed and new policies developed | 5 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Corporate services | Municipal institutional development and transformation | Build Capable work force to deliver services | 21 | 2.1.2.2 Number of funded vacant post filled by 30 June 2023 | 21 | 11 | ACHIEVED |  | Appointment letters & Listing of appointments |  |  | NOT DUE THIS QUARTER
Corporate services | Municipal institutional development and transformation | Build Capable work force to deliver services | 1 | 2.1.2.3 Number of Employee Wellness Campaign held by 30/06/23 | 1 |  | NOT DUE THIS QUARTER |  |  |  | X1 | ACHIEVED |  | Attendance Register
Corporate services | Municipal institutional development and transformation | Ensure sustainable working environment | 18 | 2.1.2.4 Number of lease agreement for Municipal Properties (Rental Houses) | 18 |  | NOT DUE THIS QUARTER |  |  |  | 18 2 SUBMITTED | NOT ACHIEVED |  | Individual Signed Lease Agreements
Corporate services | Municipal institutional development and transformation | Review and adoption of the organisational structure for 2023/24 financial year | 1 | 2.1.2.5 Number of adopted reviewed Organogram | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Corporate services | Municipal institutional development and transformation | Sitting of Local Labour Forum | 4 | 2.1.2.6 Number of LLF meetings conducted | 4 | 1 | ACHIEVED |  | Minutes & attendance Registers |  | 1 | ACHIEVED |  | Minutes & attendance Registers
Corporate services | Municipal institutional development and transformation | Review of a Workplace Skills Plan (WSP) for 2023/24 Financial Year | 1 | 2.1.3.1 Number of approved Workplace Skills Plan submitted to LG SETA | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Corporate services | Municipal institutional development and transformation | Provision of Training for f Councilors and officials | 16 | 2.1.3.2 Number of Officials &councilor’s trained | 30 |  | NOT DUE THIS QUARTER |  |  |  | 11 Councilors | ACHIEVED |  | Attendance registers
Corporate services | Municipal institutional development and transformation | Compile and employment equity report in the year ended 2023 | 1 | 2.1.3.3 Number of employment equity report compiled | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER

## BUDGET & TREASURY
KEY PERFORMANCE AREA 3: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT (SOUND FINANCIAL MANAGEMENT)
DEPARTMENT | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY MEASURABLE PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGETS |  |  |  |  | QUARTERLY TARGETS |  |  |  |  | CORRECTIVE MEASURES TO BE TAKEN
[6 empty] | QUARTER 1 |  |  |  |  | QUARTER 2
[6 empty] | Target | Actual Achievement | Budget | Means of verification | Reasons of Variances | Target | Actual Achievement | Budget | Means of verification | Reasons for Varisnce
Objective:
Budget & Treasury | Municipal financial viability and management ( sound financial management) | To ensure that procurement of services is concluded within 90 Days (Bids) | New Indicator | 3.1.1 Percentage of Bid awarded within 90 Days (per 80/20 procurement process) | 100% | 100% Bid Awarded | ACHIEVED |  | Tender Register/Listing & Appointment Letters |  | 100% Bid Awarded | NOT ACHIEVED |  | Tender Register/Listing & Appointment Letters | DELAYS IN CONVENING BID COMMITTES | PROCESS WILL RESUME AFTER THE BID COMMITTEE CONVENES
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 1 Annual Financial Statements prepared and submitted to Auditor General in the year ended June 2023 | 1 | 3.1.1.1 Number of Annual Financial Statement submitted to Auditor General | x1 | x1 | ACHIEVED |  | Proof of submission (e-mail) and signed copy of annual financial statement |  |  | NOT DUE THIS QUARTER
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 1 Draft and Final Budgets prepared; tabled to Council and Submitted to Treasury in the year ended June 2023 | 1 | 3.1.2.1 Number of municipal draft &final annual budget adopted | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 1 Adjustment budget reviewed, adopted by Council and submitted to Treasury in the year ended June 2023. | 1 | 3.1.2.2 Number of municipal adjustment budget adopted | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Investment reconciliation prepared in the year ended June 2023 | 12 | 3.1.3.1 Number of monthly investments reconciliation | x12 | x3 | ACHIEVED | - | Signed Investment Registers |  | x3 | ACHIEVED | - | Signed Investment Registers
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Grant reconciliation to be prepared in the year ended 2023 | 12 | 3.1.3.2 Number of monthly grant reconciliation | x12 | x3 | ACHIEVED | - | Signed copies of grant reconciliations |  | x3 | ACHIEVED | - | Signed copies of grant reconciliations
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 creditors reconciliations prepared in the 2023 Year end | 12 | 3.1.3.3 Number of monthly creditors reconciliation | x12 | x3 | ACHIEVED | - | Signed copies of the creditors reconciliations |  | x3 | ACHIEVED | - | Signed copies of the creditors reconciliations
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Valuation roll reconciliations to be prepared in the year ended 2023 | 12 | 3.1.4.1 Number of monthly valuation roll reconciliation | x12 | x3 | ACHIEVED | - | Signed copies of valuation roll reconciliations |  | x3 | ACHIEVED | - | Signed copies of valuation roll reconciliations
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Debtors reconciliation to be prepared in the year ended 2023 | 12 | 3.1.4.2 Number of monthly debtors reconciliation | x12 | x3 | NOT ACHIEVED | - | Signed copies debtors reconciliations |  | x3 | NOT ACHIEVED | - | Signed copies debtors reconciliations
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Supply Chain Management reports submitted to the Mayor; Cogta and Provincial Treasury in the year ended June 2023 | 12 | 3.1.5.1 Number of monthly and quarterly Supply Chain processes reports | x12 | x3 | ACHIEVED |  | Compile monthly & quarterly reports |  | x3 | ACHIEVED |  | Compile monthly & quarterly reports
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 1 Procurement Plans prepared and submitted in the 2022/23 Financial year | 1 | 3.1.5.2 Number of adopted and updated SCM framework | x1 | x1 | ACHIEVED |  | Proof of submission (e-mail) and signed procurement plan. |  |  | NOT DUE THIS QUARTER
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 4 times the Contract register is reviewed and updated in the 2023 Financial Year | 4 | 3.1.5.3 Number of contract register reviewed and updated | x4 | 1x update | ACHIEVED | - | Signed copies of contract registers |  | 1x update | NOT ACHIEVED | - | Signed copies of contract registers
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 C schedule (S71) Reports prepared and submitted to Mayor and Provincial Treasury in the year ended June 2023 | 12 | 3.1.6.1 Number of monthly Section71 reports compiled | x12 | Compile 3 reports for S71 reports | ACHIEVED |  | Proof of submission (email) and reports |  | Compile 3 reports for S71 reports | ACHIEVED |  | Proof of submission
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 1 section 72 reports completed and submitted to council in the year ended June 2023 | 1 | 3.1.6.2 Section 72 reports completed and submitted to council | x1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 4 section 52 reports prepared and submitted to council in the year ended June 2023 | 4 | 3.1.6.3 Number of annual financial reports | x4 | x1 | ACHIEVED |  | Proof of submission (e-mail) and reports |  |  | ACHIEVED |  | VAT 201 statements
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 VAT returns submitted to SARS in the year ended June 2023 | 12 | 3.1.6.4 Number of VAT returns submitted to SARS | x12 | x3 | NOT ACHIEVED |  | VAT 201 statements |  |  | ACHIEVED
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Assets Reconciliation prepared in the year ended 2023 | 12 | 3.1.6.5 Number of monthly assets reconciliation | x12 | x3 | ACHIEVED |  | Signed copies asset reconciliations |  | x1 | ACHIEVED |  | Proof of submission (e-mail) and reports
Budget & Treasury | Municipal financial viability and management ( sound financial management) | 12 Bank reconciliation prepared in the year ended 2023 | 12 | 3.1.6.6 Number of monthly bank reconciliation | x12 | x3 | ACHIEVED |  | Signed copies bank reconciliations |  | x3 | ACHIEVED |  | VAT 201 statements

## CORPORATE & MM
[6 empty] | KEY PERFORMANCE AREA 4: GOOD GOVERNANCE AND PUBLIC PARTICIPATION (PUTTING PEOPLE FIRST) |  |  |  |  | KEY PERFORMANCE AREA 4: GOOD GOVERNANCE AND PUBLIC PARTICIPATION (PUTTING PEOPLE FIRST)
DEPARTMENT | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY MEASURABLE PERFORMANCE INDICATO | ANNUAL TARGET | QUARTERLY TARGETS |  |  |  |  | QUARTERLY TARGETS |  |  |  |  | CORRECTIVE MEASURES TO BE TAKEN
[6 empty] | QUARTER 1 |  |  |  |  | QUARTER 2
[6 empty] | Target | Actual Achievement | Budget | Means of verification | Reasons for Variance | Target | Actual Achievement | Budget | Means of verification | Reasons for Variance
Objective:
Corporate &Community Services | Good governance and public participation (putting people first) | 24 Public meetings conducted during 2022/23 | 24 | 4.1.1.1 Number of public meetings (per ward) conducted | 24 | x6 | ACHIEVED |  | Agenda, Minutes &Attendance register |  | x6 | ACHIEVED |  | Agenda, Minutes &Attendance register
Corporate &Community Services | Good governance and public participation (putting people first) | 6 Public meetings conducted during 2022/23 | 0 | 4.1.1.2 Number of Izimbizo meeting conducted | 6 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Corporate &Community Services | Good governance and public participation (putting people first) | 72 ward committee meetings held during end of 2022/23 | 72 | 4.1.1.3 Number of quarterly meetings reports per ward (ward committee) | 72 | x18 | ACHIEVED |  | Minutes & Register |  | x18 | ACHIEVED |  | Minutes & Register
Corporate &Community Services | Good governance and public participation (putting people first) | 4 Local Task Team (OSS) Meetings held during 2022/23 | 0 | 4.1.1.4 Number of Local Task Team meetings held | 4 | x1 | ACHIEVED |  | Quarterly report |  | x1 | ACHIEVED |  | Quarterly report
Office of the Municipal Manager | Ensure a financially visible and sustainable municipality | To ensure that procurement of services is concluded within 90 Days (Bids) | New Indicator | 4.1.1.5 Percentage of Bid awarded within 90 Days (per 80/20 procurement process) | 100% | 100% Bid Awarded | ACHIEVED |  | Tender Register/Listing & Appointment Letters |  | 100% Bid Awarded | NOT ACHIEVED |  | Tender Register/Listing & Appointment Letters | DELAYS IN CONVENING BID COMMITTES | PROCESS WILL RESUME AFTER THE BID COMMITTEE CONVENES
Office of the Municipal Manager | Good governance and public participation (putting people first) | 2 IDP RF meetings conducted in the financial year 2022/23 | 2 | 4.1.1.6 Number of the IDP RF functionality. | 2 |  | NOT DUE THIS QUARTER |  |  |  |  | ACHIEVED
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 radio interviews conducted by the Executive Municipality in the end of 2022/23 Financial Year | 4 | 4.1.2.1 Number of radio slots conducted | 4 | x1 | ACHIEVED |  | Podcast & signed invoice |  | x1 | ACHIEVED |  | Podcast & signed invoice
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 Newsletters published in the 2022/23 financial year | 0 | 4.1.2.2 Number of newsletters published | 4 | x1 | ACHIEVED |  | Copy of the newsletter |  | x1 | NOT ACHIEVED |  | Copy of the newsletter | TARGET WAS NOT MET DUE TO FINANCIAL CONSTRAINTS
Office of the Municipal Manager | Good governance and public participation (putting people first) | 18 banners procured in the 2022/23 financial year | 0 | 4.1.2.3 (a) Number of marketing material procured (banners) | 4 | X1 | ACHIEVED | R 33 000 | Invoice |  | X1 | ACHIEVED | R 33 000 | Invoice
Office of the Municipal Manager | Good governance and public participation (putting people first) | 10 000 Calendars procured in the 2022/23 financial year | 0 | 4.1.2.3 (b) Number of marketing material procured (calendars & diaries) | 10 000 calendars & 200 diaries |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 121 Political bears wall pictures in the year ended 30 June 2023 | 0 | 4.1.2.4 Number of photography services conducted | 121 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 prepared, adopted and submitted IDP 2023/24 Financial Year | 2022/2023 IDP | 4.1.3.1 Number of prepared, adopted and submitted IDP | Review and adopt 2023/24 IDP |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 prepared, adopted and submitted SDBIP 2023/24 Financial Year | 2023/2024 SDBIP | 4.1.3.2 2023/2024 Service Delivery and Budget Implementation Plan | 1 Adoption of SDBIP |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 Prepared, adopted and submitted IDP& Budget Process Plan for 2023/24 Financial Year | 1 | 4.1.3.3 Number of prepared, adopted and submitted IDP& Budget Process Plan | 1 | 1 | ACHIEVED |  | Council Resolution |  | 1 | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 Annual Performance Reports prepared and submitted to AG and relative authorities | 1 | 4.1.3.4 Number of Annual Performance Reports prepared and submitted to AG and relative authorities | 1 | 2021/22 APR | ACHIEVED |  | Extract for APR & Council Resolution |  | 2021/22 APR | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 reviewed and adopted performance management system | 1 | 4.1.3.5 Number of reviewed and adopted performance management system policy | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 Oversight reports prepared and submitted to MPAC for the Year ended June 2022 | 1 | 4.1.3.6 Number of oversight reports prepared and submitted to MPAC | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 Quarterly performance reports adopted by the council in the 2022/23 financial year | 0 | 4.1.3.7 Number of quarterly Performance Reports generated and submitted to Internal Audit | 4 | x1 | ACHIEVED |  | Extract of the report & proof of submission from Internal Auditor |  | x1 | ACHIEVED |  | Extract of the report & proof of submission from Internal Auditor
Office of the Municipal Manager | Good governance and public participation (putting people first) | 12 Council meetings held in the 2022/23 Financial Year | 4 | 4.1.4.1 Number of legislated Council meetings seated | 4 | X1 | ACHIEVED |  | Notice of meetings & Attendance Register |  | X1 | ACHIEVED |  | Notice of meetings & Attendance Register
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 Audit committee meetings Held in the end of 2022/23 Financial Year | 4 | 4.1.4.2 Number of audit committee quarterly meetings | 4 | x1 | ACHIEVED |  | Notice of meetings, Minutes & Attendance Register |  | x1 | ACHIEVED |  | Notice of meetings, Minutes & Attendance Register
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 Risk Management Meetings held in the 2022/23 Financial Year | 4 | 4.1.4.3 Number of risk management meetings conducted | 4 | x1 | ACHIEVED |  | Notice of meetings, Minutes & Attendance Register |  | x1 | NOT ACHIEVED |  | Notice of meetings, Minutes & Attendance Register | MEETING WAS POSTPONED DUE TO THE MEETING SCHEDULE CONFLICT | MEETING WILL CONVENE IN JANUARY 2023
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 conduct Annual Risk Assessment & Annual Fraud Risk Assessment for 2023/24 | 1 | 4.1.4.4 Number of Annual Risk Assessment & Annual Fraud Risk Assessment conducted | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 12 Internal audit reports generated in the year ending June 2023 | 12 | 4.1.4.5 Number of internal audit report generated. | 12 | x3 | ACHIEVED |  | Extract of reports |  | x3 | ACHIEVED |  | Extract of reports
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 Internal Audit Charter approved by Audit Committee in the Year 2022/23 Financial Year | 1 | 4.1.4.6 Number of internal audit charter approved by audit committee | 1 | x1 | ACHIEVED |  | Audit Committee Resolution on approved Charter |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 Audit Committee Charter reviewed and approved by Council in the m 2022/23 Financial Year | 1 | 4.1.4.7 Number of audit committee charter reviewed and approved by council | 1 | x1 | ACHIEVED |  | Council resolution on approved Charter |  | x1 | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 audit committee reports tabled to Council for the year ended 30 June 2023 | 4 | 4.1.4.8 Number of audit committee reports tabled to council | 4 | x1 | NOT ACHIEVED |  | Council Resolution and minutes | Due to the on going AG Audit & Managerial commitments, the Chairperson was unable to present a comprehensive report on the status of operations. | x1 | NOT ACHIEVED |  | Council Resolution and minutes | Due to the on going AG Audit & Managerial commitments, the Chairperson was unable to present a comprehensive report on the status of operations. | Audit Committee Reports will be tabled to the Councilin the 2nd Quarter
Office of the municipal manager | Good governance and public participation (putting people first) | 1 internal Audit Annual Plan developed for 2022/23 Financial Year | 1 | 4.1.4.9 Number of internal audit annual plan developed | 1 | Develop Internal Audit Annual Plan | ACHIEVED |  | Audit Committee Resolution and copy of Internal Audit Annual Plan |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 1 action plans prepared on Audit findings and submitted to MM in 2022/23 | 1 | 4.1.4.10 Number if action plan prepared on audit findings and submitted to municipal manager | 1 |  | NOT DUE THIS QUARTER |  |  |  |  | NOT DUE THIS QUARTER
Office of the Municipal Manager | Good governance and public participation (putting people first) | 4 quarterly update of risk register generated for 2022/23 Financial Year | 4 | 4.1.4.11 Number of quarterly update for risk register conducted | 4 | x1 | ACHIEVED |  | Extract of the report & minutes |  | x1 | NOT ACHIEVED |  | Extract of the report & minutes
Office of the Municipal Manager | Good governance and public participation (putting people first) | 12 Legislated MANCO meetings seated |  | 4.1.4.12 Number of legislated MANCO meetings seated | 12 | x3 | ACHIEVED |  | Extract of minutes & attendance register |  | x3 | ACHIEVED |  | Extract of minutes & attendance register

## CORPORATE & COMMUNITY
KEY PERFORMANCE AREA 5: LOCAL ECONOMIC AND SOCIAL DEVELOPMENT (SERVICE DELIVERY)
DEPARTMENT | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY MEASURABLE PERFORMANCE INDICATOR T | ANNUAL TARGET | QUARTERLY TARGETS |  |  |  |  | QUARTERLY TARGETS |  |  |  |  | CORRECTIVE MEASURES TO BE TAKEN
[6 empty] | QUARTER 1 |  |  |  |  | QUARTER 2
[6 empty] | Target | Actual Achievement | Budget | Means of verification | Reasons for Variance | Target | Actual Achievement | Budget | Means of verification | Reasons of Variances
Objective:
Corporate & Community Services | Local Economic Development (service delivery) | 4 vulnerable groups forums meetings / workshops in the 2022/23 financial year | 4 | 5.1.1.1 Number of meetings/ workshop for forums of vulnerable groups implemented | 4 | x1 | ACHIEVED |  | Agenda, Minutes & Attendance Registers |  | x1 | ACHIEVED |  | Agenda, Minutes & Attendance Registers
Corporate & Community Services | Local Economic Development (service delivery) | 8 Special Programmes conducted | x7 | 5.1.1.2 Number of special programmes coordinated to empower the vulnerable groups | 8 | x2 | ACHIEVED |  | Report & Register |  | x2 | ACHIEVED |  | Report & Register
Corporate & Community Services | Local Economic Development (service delivery) | 4 book exchange Programmes in the 2022/23 Financial Year | 4 | 5.2.1.1 Number of book exchange programmes | 4 | x1 | ACHIEVED |  | Quarterly report |  | x1 | ACHIEVED |  | Quarterly report
Corporate & Community Services | Local Economic Development (service delivery) | 4 library orientation and outreach programs held during 2022/23 Financial Year | 3 | 5.2.1.2 Number of library orientation and outreach programmes | 4 | x1 | ACHIEVED |  | Agenda, Minutes & Attendance Registers |  | x1 | ACHIEVED |  | Agenda, Minutes & Attendance Registers
Corporate & Community Services | Local Economic Development (service delivery) | 8 road blocks conducted in the 2022/23 Financial Year | 12 | 5.4.3.1 Number of road blocks conducted | 8 | x2 | ACHIEVED |  | Quarterly report |  | x2 | ACHIEVED |  | Quarterly report